## Dashboard
KZ-TB12 ¦ Simulated Project Controls Dashboard
Scenario status date | 2026-10-26 17:00
Baseline finish | 2027-01-04 17:00
Simulated forecast finish | 2027-01-09 17:00
Simulated forecast slip | 5 | calendar days
BAC | 1200000 |  | PV | 263125 | EV | 251593.75 | AC | 264835.5263
SPI | 0.95618 |  | CPI | 0.95 | EAC | 1263157.8947 | VAC | -63157.8947
Interpretation
SPI < 1.00 indicates simulated delay against the baseline. CPI < 1.00 indicates simulated cost inefficiency. These are scenario outputs, not actual project records.

## Read Me
KZ-TB12 ¦ Simulated Project Controls Reporting Package
Purpose | Hypothetical status-date controls scenario derived from the baseline XER.
Status date | 2026-10-26 17:00
Scenario note | All progress, budget, actual cost, forecast, and risk values in this workbook are simulated assumptions—not genuine execution updates.
Workbook tabs
Dashboard | Executive KPI view with EVM and progress charts
Activity Update | Activity-level simulated status and forecast
WBS Summary | Budget, PV, EV, AC and variance by workstream
Risks | Simulated risk register with owners and mitigations
Assumptions | Scenario assumptions and data limitations

## Activity Update
Activity Update ¦ Simulated Status Date 26 Oct 2026
Activity ID | Activity Name | Workstream | Baseline Start | Baseline Finish | Forecast Finish | Planned Days | Budget | Status | Progress % | PV | EV | AC | Schedule Var (days) | Total Float (hr) | Basis / Comment
KZ.TB10 | Project Inauguration | Project controls / start-up | 2026-09-12 07:00 | 2026-09-12 07:00 | 2026-09-12 07:00 | 0 | 0 | Complete | 100% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB20 | Project Material Settlement and Site Preparation | Project controls / start-up | 2026-09-12 07:00 | 2026-09-16 17:00 | 2026-09-16 17:00 | 5 | 28125 | Complete | 100% | 28125 | 28125 | 29605.2632 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB30 | Inspection by ASE | Project controls / start-up | 2026-09-17 07:00 | 2026-09-17 17:00 | 2026-09-17 17:00 | 1 | 5625 | Complete | 100% | 5625 | 5625 | 5921.0526 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB100 | Concrete Bedding Start | Concrete bedding | 2026-09-19 07:00 | 2026-09-19 07:00 | 2026-09-19 07:00 | 0 | 0 | Complete | 100% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB110 | Compaction of Sand Base | Concrete bedding | 2026-09-19 07:00 | 2026-09-19 17:00 | 2026-09-19 17:00 | 1 | 25000 | Complete | 100% | 25000 | 25000 | 26315.7895 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB120 | Installation of Formwork | Concrete bedding | 2026-09-20 07:00 | 2026-09-20 17:00 | 2026-09-20 17:00 | 1 | 25000 | Complete | 100% | 25000 | 25000 | 26315.7895 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB130 | Concreting of Bedding - B7.5 | Concrete bedding | 2026-09-28 07:00 | 2026-09-28 17:00 | 2026-09-28 17:00 | 1 | 25000 | Complete | 100% | 25000 | 25000 | 26315.7895 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB140 | Concrete Bedding Inspection by ASE | Concrete bedding | 2026-09-29 07:00 | 2026-09-29 17:00 | 2026-09-29 17:00 | 1 | 25000 | Complete | 100% | 25000 | 25000 | 26315.7895 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB150 | Concrete Bedding Finish | Concrete bedding | 2026-09-29 17:00 | 2026-09-29 17:00 | 2026-09-29 17:00 | 0 | 0 | Complete | 100% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS200 | Foundation Start | Project controls / start-up | 2026-09-30 07:00 | 2026-09-30 07:00 | 2026-09-30 07:00 | 0 | 0 | Complete | 100% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS210 | Reinforcement Works | Project controls / start-up | 2026-09-30 07:00 | 2026-10-01 17:00 | 2026-10-01 17:00 | 2 | 11250 | Complete | 100% | 11250 | 11250 | 11842.1053 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS220 | Installation of Formwork | Project controls / start-up | 2026-10-03 07:00 | 2026-10-06 17:00 | 2026-10-06 17:00 | 4 | 22500 | Complete | 100% | 22500 | 22500 | 23684.2105 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS230 | Concreting - B25 | Project controls / start-up | 2026-10-07 07:00 | 2026-10-10 17:00 | 2026-10-10 17:00 | 3 | 16875 | Complete | 100% | 16875 | 16875 | 17763.1579 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS240 | Installation of Formwork - Top | Project controls / start-up | 2026-10-11 07:00 | 2026-10-14 17:00 | 2026-10-14 17:00 | 4 | 22500 | Complete | 100% | 22500 | 22500 | 23684.2105 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS250 | Concreting - B25- Top | Project controls / start-up | 2026-10-15 07:00 | 2026-10-18 17:00 | 2026-10-18 17:00 | 3 | 16875 | Complete | 100% | 16875 | 16875 | 17763.1579 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS260 | Application of Bitumen TechnoNicol Primer | Project controls / start-up | 2026-10-19 07:00 | 2026-10-19 17:00 | 2026-10-19 17:00 | 1 | 5625 | Complete | 100% | 5625 | 5625 | 5921.0526 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS270 | Application of Bitumen Mastic 90/10 | Project controls / start-up | 2026-10-20 07:00 | 2026-10-20 17:00 | 2026-10-20 17:00 | 1 | 5625 | Complete | 100% | 5625 | 5625 | 5921.0526 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS280 | Backfilling- 43 Layer | Project controls / start-up | 2026-10-21 07:00 | 2026-10-24 17:00 | 2026-10-28 17:00 | 3 | 16875 | In progress | 65% | 16875 | 10968.75 | 11546.0526 | 4 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS290 | Foundation Inspection by ASE, BAEC | Project controls / start-up | 2026-10-25 07:00 | 2026-10-25 17:00 | 2026-10-29 17:00 | 1 | 5625 | Not started | 0% | 5625 | 0 | 0 | 4 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS300 | Foundation Finish | Project controls / start-up | 2026-10-25 17:00 | 2026-10-25 17:00 | 2026-10-29 17:00 | 0 | 0 | Complete | 100% | 0 | 0 | 0 | 4 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB160 | Concrete Bedding of FM 1 Foundation Start | Project controls / start-up | 2026-10-26 07:00 | 2026-10-26 07:00 | 2026-10-26 07:00 | 0 | 0 | Complete | 100% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB170 | Compaction of Sand Base | Project controls / start-up | 2026-10-26 07:00 | 2026-10-26 17:00 | 2026-10-26 17:00 | 1 | 5625 | Complete | 100% | 5625 | 5625 | 5921.0526 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB180 | Installation of Formwork | Project controls / start-up | 2026-10-27 07:00 | 2026-10-27 17:00 | 2026-10-27 17:00 | 1 | 5625 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB190 | Concreting of Bedding - B7.5 | Project controls / start-up | 2026-11-04 07:00 | 2026-11-04 17:00 | 2026-11-04 17:00 | 1 | 5625 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB200 | Concrete Bedding Inspection by ASE | Project controls / start-up | 2026-11-05 07:00 | 2026-11-05 17:00 | 2026-11-05 17:00 | 1 | 5625 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
KZ.TB210 | Concrete Bedding Finish | Project controls / start-up | 2026-11-05 17:00 | 2026-11-05 17:00 | 2026-11-05 17:00 | 0 | 0 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS310 | Foundation Start | FM1 foundation | 2026-11-07 07:00 | 2026-11-07 07:00 | 2026-11-07 07:00 | 0 | 0 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS320 | Reinforcement Works | FM1 foundation | 2026-11-07 07:00 | 2026-11-08 17:00 | 2026-11-08 17:00 | 2 | 72000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS330 | Installation of Formwork | FM1 foundation | 2026-11-09 07:00 | 2026-11-12 17:00 | 2026-11-12 17:00 | 4 | 144000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS340 | Concreting - B25 | FM1 foundation | 2026-11-14 07:00 | 2026-11-16 17:00 | 2026-11-16 17:00 | 3 | 108000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS350 | Installation of Formwork - Top | FM1 foundation | 2026-11-17 07:00 | 2026-11-21 17:00 | 2026-11-21 17:00 | 4 | 144000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS360 | Concreting - B25- Top | FM1 foundation | 2026-11-22 07:00 | 2026-11-24 17:00 | 2026-11-24 17:00 | 3 | 108000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS370 | Application of Bitumen TechnoNicol Primer | FM1 foundation | 2026-11-25 07:00 | 2026-11-25 17:00 | 2026-11-25 17:00 | 1 | 36000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS380 | Application of Bitumen Mastic 90/10 | FM1 foundation | 2026-11-26 07:00 | 2026-11-26 17:00 | 2026-11-26 17:00 | 1 | 36000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS390 | Backfilling- 2 Layer | FM1 foundation | 2026-11-28 07:00 | 2026-11-28 17:00 | 2026-11-28 17:00 | 1 | 36000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS400 | Foundation Inspection by ASE, BAEC | FM1 foundation | 2026-11-29 07:00 | 2026-11-29 17:00 | 2026-11-29 17:00 | 1 | 36000 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
FS.MS410 | Foundation Finish | FM1 foundation | 2026-11-29 17:00 | 2026-11-29 17:00 | 2026-11-29 17:00 | 0 | 0 | Not started | 0% | 0 | 0 | 0 | 0 | 0 | Simulated status based on baseline timing; validate with field records.
ABD.C200 | Preparation of As Built Document | Documentation / handover | 2026-11-30 07:00 | 2026-12-16 17:00 | 2026-12-21 17:00 | 15 | 60000 | Not started | 0% | 0 | 0 | 0 | 5 | 50 | Simulated status based on baseline timing; validate with field records.
ABD.C210 | Preparation of WEP | Documentation / handover | 2026-11-30 07:00 | 2026-12-22 17:00 | 2026-12-27 17:00 | 20 | 80000 | Not started | 0% | 0 | 0 | 0 | 5 | 0 | Simulated status based on baseline timing; validate with field records.
ABD.C220 | Submission of First Copy ABD | Documentation / handover | 2026-12-23 07:00 | 2026-12-23 17:00 | 2026-12-28 17:00 | 1 | 4000 | Not started | 0% | 0 | 0 | 0 | 5 | 0 | Simulated status based on baseline timing; validate with field records.
ABD.C230 | Submission of 5 Copy ABD | Documentation / handover | 2026-12-24 07:00 | 2027-01-04 17:00 | 2027-01-09 17:00 | 10 | 40000 | Not started | 0% | 0 | 0 | 0 | 5 | 0 | Simulated status based on baseline timing; validate with field records.
ABD.C240 | Project Hand Over with ABD | Documentation / handover | 2027-01-04 17:00 | 2027-01-04 17:00 | 2027-01-09 17:00 | 4 | 16000 | Not started | 0% | 0 | 0 | 0 | 5 | 0 | Simulated status based on baseline timing; validate with field records.

## WBS Summary
WBS Summary ¦ Simulated Performance
Workstream | Budget | PV | EV | AC | SPI | CPI | Variance at Completion | Comment
Project controls / start-up | 180000 | 163125 | 151593.75 | 159572.3684 | 0.92931 | 0.95 | -9473.6842 | Simulated; not from actual cost records.
Concrete bedding | 100000 | 100000 | 100000 | 105263.1579 | 1 | 0.95 | -5263.1579 | Simulated; not from actual cost records.
FM1 foundation | 720000 | 0 | 0 | 0 | 0 | 0 | 720000 | Simulated; not from actual cost records.
Documentation / handover | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | Simulated; not from actual cost records.

## Risks
Simulated Risk Register
Risk ID | Risk / Opportunity | Category | Probability | Impact | Score | Owner | Mitigation / Response | Trigger / Leading Indicator | Status
R-01 | External inspection / approval interface | Interface | Medium | High | 6 | Construction Manager | Pre-book ASE / BAEC inspections; maintain inspection release log. | Inspection request not accepted 48h before need date. | Open
R-02 | Documentation handover compression | Interface | Medium | High | 6 | Document Controller | Start ABD / WEP package early; weekly document burn-down. | First copy not ready by 20 Dec. | Open
R-03 | Resource / productivity uncertainty | Controls | High | Medium | 6 | Project Controls Manager | Load resource plan and update actual hours weekly. | Actual hours exceed plan by 10%. | Open
R-04 | Calendar / holiday exception mismatch | Planning | Medium | Medium | 4 | Lead Planner | Validate calendar exceptions and 60h lags with site team. | Logic dates differ from field constraints. | Open
R-05 | Weather / curing / access | Execution | Medium | Medium | 4 | Site Manager | Add look-ahead constraints and weather allowance. | Concrete or bitumen work interrupted. | Open

## Assumptions
Scenario Assumptions & Data Limitations
ID | Assumption | Value | Rationale
A-01 | Status date | 26 Oct 2026, 17:00 local time | Selected as a plausible reporting cut-off after the first foundation package and before FM1 works.
A-02 | Budget at completion (BAC) | $1,200,000 simulated | No cost data is present in the XER; budget is a hypothetical control total for demonstrating EVM.
A-03 | Workstream budgets | Controls $180k; bedding $100k; FM1 $720k; documentation $200k | Allocated to create an internally consistent scenario.
A-04 | Actual progress | Activity-level progress inferred from baseline timing with selected slippage overrides | Not a genuine progress update; requires field validation.
A-05 | Actual cost | AC calculated at EV / 0.95 | Creates a simulated CPI of 0.95 to demonstrate cost performance reporting.
A-06 | Forecast finish | Physical package +4 days; documentation +5 days | Illustrative forecast impact from inspection / backfill delay and handover compression.
A-07 | Missing source fields | Resources, actuals, costs, quantities, issues and risk events | These fields must be populated from project records before operational use.